## Sales and marketing
Unity Sales and marketing modules
To do list : ETA 3/9/2021
S.no |  | Key person | Status
1 | Create editable dropdowns | alex | Done
2 | Structure a clear navigation flow | Chris | Not started | Discussion on MON
3 | Create Closer dashboard | alex | Done
4 | Create teamleader dashboard | alex | Done
6 | Create Admin Dashboard(shouldn’t be very differrent from teamleader's) | alex | Done
5 | Improve on agent dashboard | Chris | Done
7 | Create criteria for mass edit of db values for any specific table | Chris | Not started
8 | Create call back scheduling funtion | Chris | Done
9 | Add popup to input reason for status change | Chris | Done
10 | Provide filter funtionality for datatables | alex | In progress
11 | Change default system time format to m-d-Y | Chris | Done
12 | Show interraction history notes on caall modal | alex | Done
13 | Mass upload of leads | Chris | Done
Include %rates 35,40, 50
Contact persons

## Simplicity
Simplicity
1 | Finish on uploads
2 | Link doc folder to company(lead/client)
3 | Extend lead profile to include additional client info
4 | Set up client table(DB)
5 | Set up debtor table(db)
6 | Set up debtor account